## Introduction
Shannon Flood Risk State Agency Co-ordination Working Group
Work Programme 2025
The Group’s extensive Work Programme demonstrates the scale of planned and ongoing work by all State Agencies that may help to mitigate flood risk aloong the River Shannon. This Work Programme is structured under the following themes of activity:
Physical Works
Maintenance:
Maintenance of Infrastructure
Maintenance of Channels
Water Management:
Water Level and Flow Regulation
Hydrometric Monitoring
Regulatory Functions
Policy and Planning:
Mapping, Planning and Emergency
WFD and Climate Change

## Physical Works
Physical Works | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Responsibilities
ESB
| Ardnacrusha concrete repairs | Ardnacrusha Dam. | January - December 2025 | N/A | Concrete repairs completed | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Parteen Weir concrete repairs | Parteen Weir. | January - December 2025 | N/A | Concrete repairs completed | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| AA2 Generator rotor pull and Major overhaul including equipment upgrade | Ardnacrusha Generating Station. | April - September 2025 | N/A | Inspection completed and condition assessed. | Unit 2 is reliable to assist regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including ensuring that water can be diverted from the River Shannon through Ardnacrusha Headrace | y
| Painting and Overhauling of Parteen Weir Canal Gate Superstructure | Ardnacrusha Generating Station. | April - September 2025 | N/A | Superstructure steel work inspected, repaired as necesssary and painted at Canal Gates | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Annual Overhaul of Parteen Weir Spillway and Canal gates | Parteen Weir. | April - September 2025 | N/A | Spillway nd Canal Gates Overhauled | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Removal of Trees on tailrace Canal near navigations locks | Tailrace | Jan- March 2025 , September to December 2025 | N/A | Trees Removed | Safety Improvement for Navigation thtough navigation locks and tailrace canal | y
| Embankment Concrete Plating Repairs Ardnacrusha Headrace | Ardancrusha Headrace Canal | Jan - April 2025, Sepetember - December 2025 | N/A | Concrete Plating Repaired | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Steelwork Repairs at Athlone Breakwater | Athlone Weir | July - December 2025 | N/A | Repair of Breakwater Strucutre | Increasing Lifespan of Structure which protects navigation channel against turbulence from Athlone Sluice Discharges | y
| Site Investigation Works on Ardnacrusha Category A Earthen Embankment Dams | Fort Henry and Ardclooney Embankments upstream of Parteen Weir. Ardnacrusha Embankments on headrace canal. | June - December 2025 | N/A | Site Investigation Completed | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| New Relief Holes at Left Retaining Wall of Lower Ardnacrusha Navigation Lock | Ardnacrusha Dam. | April - July 2025 | N/A | Relief Holes Installed further relieving water pressure behind retaining walls | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace.
| Black River Culvert Cleaning | Parteen Weir. | May- June 2025 | N/A | Black River Culvert Cleaned and Structural Inspection Carried out with any defects identified repaired | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace.
| Blackwater Culvert Fishpass Maintainence | Parteen Weir. | April - December 2025 | N/A | Maintainence and Upgrade Works to Fishpass | Improvement of Fish Passage
| Navigation Lock Gates Overhaul | Ardnacrusha Dam. | September - Dcember 2025 | Permission being recived to close Navigation Locks for Duration of Overhaul | Navigation Gates Overhauled | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace.
| Design and Repair to Bridge Half Joints on Headrace Bridges | Ardnacrusha Headrace, Tailrace, Killaloe | Summer - Autumn 2025 | N/A | Half Joints Sealed | Half Joints on Bridges Sealed and Bridge Perfomance Improved
Waterways Ireland
| Design of a fish pass and design of re-instatement of the weir | Tarmonbarry | Ongoing consultation with landowner and development of overall design in 2025 | Planning permission required | Work to be complete by 2030 | Improved functioning of the weir / reinstate original structure
Irish Water
| Foul/Combined Sewer Drainage Upgrades | Athlone | Capital Maintenance & Sewer Upgrades 2021-2025. Construction Stage of large Wastewater Network Infrastruture upgrades to commenced in Q1 2023. Works will be ongoing in 2025. | N/A | Work on upgrades underway | When complete, there will be a reduced risk of road/property sewer flooding within urban catchment.
Office of Public Works/Local Authorities
Existing Programme of Flood Relief Projects at various stages between design, development, planning and construction. | Progress work on Flood Relief Schemes | A total of 38 flood relief schemes are planned for Shannon River Basin District over the lifetime of the National Development Plan (NDP) to 2030. 26 schemes are currently being progressed with schemes at construction in Athlone and Springfield. In November, preliminary works commenced on site at the flood relief scheme for King's Island in advance of the main works. This brings the number of schemes at construction to three. | During the lifetime of the NDP Programme of Investment to 2030, the OPW and Local Authorities will continue to work together to advance the first 26 of these projects. The remaining 12 projects are scheduled to be progressed under the NDP. | Various consents | As per individual project milestones | Protection of properties, land and infrastructure from future flooding. | n
All County Councils
Raising of Roads, Building of embankments, Installation of Culverts and other flood relief works funded by the OPW or DTTAS See examples below | Implementation of any investigations, remedial actions, reinstatement or repairs on arterial network which are deemed to be required. | https://www.floodinfo.ie/minor-works/ | Throughout the year. | Possible requirement for National Parks and Wildlife, Inland Fisheries, OPW & land owners for certain works. | Varies by activity | Protecting propoerties and land from flooding and ensuring access | y
Galway County Council
Flood Relief Scheme | Public Exhibition of Ballinasloe FRS | Ballinasloe | 2025 | Consultants completion of the EIAR and Options report | Public exhibition phase of the project completed n 2024. | Progression to commencement of construction in 2026 | n
Leitrim County Council
Flood Relief Scheme | Flood Relief Scheme Dromahaire | Dromahaire | Design Consultant appointed to the scheme. Design works underway. Estimated to advertise for planning approval end of Q1 2025 | Planning approval required plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owners for certain works | Construction of new flood defences. | This option provided will protect 22 properties identified as being at risk of flooding within the 1% AEP event | n
Flood Relief Scheme | Flood Relief Scheme Carrick on Shannon | Carrick on Shannon | Design Consultant appointed to the scheme. Design works underway. Estimated to advertise for planning approval in Q3 2025 | Planning approval required plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owners for certain works | Construction of a 1.8km of new flood defence walls and 846m of new embankment, Pumping stations and flood gates. | This option provides will protect 78 properties identified as being at risk of flooding within the 1% AEP event | n
Flood Relief Scheme | Flood Relief Scheme Leitrim Village | Leitrim Village | Design consultant appointed to the scheme. Design works underway. Estimated to advertise for planning approval Q4 2025 | Planning approval required plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owners for certain works | Construction of a 142m of new flood defence wall and a 498m new embankment, and a flood gate. | This will protect 58 of the 61 properties identified as being at risk of flooding within the 1% AEP event | n
Flood Relief Scheme | Flood Relief Scheme Mohill | Mohill | Awaiting determination from the OPW on the scheme progressing for Planning consent & construction. | Planning approval required plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW & land owners for certain works | Construction of rasied flood defences walls | This will reduce the risk to 7 of the 8 properties identified as being at risk in the 1% AEP event,
Flood Relief Scheme | Minor Flood Relief Scheme Keadue Road Leitrim Village | Leitrim Village | Construction work under way of rasied flood defences. Expected to be competed by end of Q1 2025 | n/a | Construction of temporary flood defence embankment and instream culvert | These temporary defences will protect 21 properties identified as being at risk of flooding until the Major FRS in Leitrim Village is completed | n
Limerick City and County Council
Flood Relief Scheme | Stage 1 - Options assessment, Scheme Development and Design | Limerick City and Environs | Q4 2025 | Public adoption of preferred design option incl requirements for NPWS, Inland Fisheries MARA and landowner agreements. | Completion of Stage 1 ( Part 2) | Indentify a viable option | n
Flood Relief Scheme | Stage 2 - Planning Process | Castleconnell | Q4 2025 | Landowner agreements and planning consent | Completion of Stage 2 | Planning approval | n
Flood Relief Scheme | Stage 1 - Options assessment, Scheme Development and Design | Adare | Q3 2025 | Landowner agreements and MARA requirements | Completion of Stage 1 | Complete Stage 1 and prepare for planning submission | n
Flood Relief Scheme | Stage 1 - Options assessment, Scheme Development and Design | Athea | Q3 2025 | Landowner agreements | Completion of Stage 1 | Complete Stage 1 and prepare for planning submission | n
Inland Fisheries Ireland
In-stream rehabiliation works on Lough Sheelin subcatchments. IFI to supervise and agree ms. | Low impact on flooding, desigend with flood conveyance in mind. Enhancement of spawing/nursery habitats for salmonids. Includes insertion of spawning gravels, restoration of sinuosity, creation of holding pools and stock proofing | River Subcatchment of Lough Sheelin Upper River Inny, Pound River, Halfcarton, Summerbank, Millbrook | May-September | Funding awarded, AA Screening/NIS/planning | The river will be enhanced for salmonids and aquatic biodiversity, where activities have been undertaken. | Improved conservation for salmonids, enhanced biodiversity | y
In-stream rehabilitation Lough Ennell . IFI to supervise and agree ms. | Low impact on flooding, designed with flood conveyance in mind. Enhancement of spawing/nursery habitats for salmonids. Includes insertion of spawning gravels, restoration of sinuosity, creation of holding pools and stock proofing | Lough Ennell sub-catchments - Buggaun River. | May-September | Funding, Screening/NIS/Planning | The river will be enhanced for salmonids and aquatic biodiversity, where activities have been undertaken. | Improved conservation for salmonids, enhanced biodiversity
In-stream rehabilitation Aughrim River (Suck Catchment) IFI to supervise and agree ms. | Low impact on flooding, designed with flood conveyance in mind. Enhancement of spawing/nursery habitats for salmonids. Includes insertion of spawning gravels, restoration of sinuosity, creation of holding pools and stock proofing | Aughrim River (Suck catchment) | May-September | Funding, Screening/AA Screening/Planning | The river will be enhanced for salmonids and aquatic biodiversity, where activities have been undertaken. | Improved conservation for salmonids, enhanced biodiversity | y
Bishops stream barrier removal, works caried out by OPW in partnership with IFI | Improvement to natural channel to facilitate fish passage and negliable impact on flooding | Edmonstown, Ballaghadreen (Lung Catchment)
Clare County Council
Shannon Town & Environs | Flood Relief Scheme | Shannon, Co. Clare | RPS Consulting Engineers appointed. Stage 1 Options Assessment | Identification of a suitable option from a technical, environmental and economic perspective. Statutory consent required thereafter plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owner engagement and agreement for certain works | Subject to detailed design, construction of new flood defences | Protection and reduced risk of flooding to properties including Town Centre, Industrial Estate and Shannon International Airport. | n
Limerick City & Environs (In conjuction with LCCC) | Flood Relief Scheme | Will protect areas of South East Clare, Westbury, Shannon Banks, Clare campus of UL, etc | Works on both sides of the river proposed so being managed on our behalf by LCCC under a Section 85 agreement | Identification of a suitable option from a technical, environmental and economic perspective. Statutory consent required thereafter plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owner engagement and agreement for certain works | Subject to detailed design, construction of new flood defences | Protection and reduced risk of flooding to properties. | n
Killlaloe (Managed by Tipp CC) | Flood Relief Scheme | Killaloe/Ballina in Clare and Tipperary | Ongoing. All works on the Ballina side so being managed by Tipperary Co Council. | Planning approval may be required plus requirement for National Parks and Wildlife, Inland Fisheries Ireland, OPW and land owners for certain works | Subject to detailed design, construction of new flood defences | Protection and reduced risk of flooding to properties. | n

## Maintenance of Infrastructure
Maintenance of Infrastructure | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Resposibilities
ESB
| Ongoing maintenance of Bellantra Sluices Structure at the outlet of Lough Allen, consisting of lubrication of sluice gate mechanisms, regular movement of gates and clearing of debris from gate openings. Note: This is a Category C structure, where a breach would pose negligible risk to life and cause limited damage. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Ongoing | N/A | Sluice structure maintained to ensure both dam safety and regulatation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon.
| Formal annual ESB inspection of Bellantra Sluices Structure, consisting of visual inspection of sluice structure, gates and operating mechanisms, test operation of gates and checking of gauges. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Summer/Autumn 2025 | N/A | Annual inspection carried out on 1 No. sluice structure. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Allen in accoradnce with ESB's Regulations and Guidelines for the Control of the River Shannon. | y
| Ongoing maintenance of Lough Allen Embankment, including grass cutting and repairs. Note: This is a Category C embankment, where a breach would pose negligible risk to life and cause limited damage. | Southwest shore of Lough Allen. | Ongoing | N/A | Approximately 1km of embankment maintained to ensure both dam safety and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | y
| Fortnightly inspections of Lough Allen Embankment. | Southwest shore of Lough Allen. | Ongoing | N/A | Safety of approximately 1km of embankment ensured and water levels regulated in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | y
| Formal annual ESB inspection of Lough Allen Embankment, comprising visual inspection of the entire length of embankment from the crest and upstream toe. | Southwest shore of Lough Allen. | Summer/Autumn 2025 | N/A | Annual inspection of approximately 1km of embankment carried out. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | y
| Ongoing maintenance of water control equipment at Bellantra Sluice Structure. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Ongoing | N/A | 2 No. sluice gates maintained to ensure both dam safety and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Water control equipment operates reliably to ensure dam safety and regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | y
| Embankment maintenance and repairs at Meelick, Whitesford and Boula, including grass cutting, drain cleaning and repairs as required. | Meelick, Whitesford and Boula Embankments on river upstream of Lough Derg. | April - September 2025 | Possible requirement for National Parks and Wildlife Service licence for certain works in Special Areas of Conservation (SAC). | Integrity and design crest level of approximately 20km of embankments maintained. | Integrity of Meelick, Whitesford and Boula Embankments maintained during floods and agricultural land protected for river levels up to the design crest level of the embankments. | y
| Fortnightly inspections of Meelick, Whitesford and Boula Embankments. | Meelick, Whitesford and Boula Embankments on river upstream of Lough Derg. | Ongoing | N/A | Integrity of approximately 20km of embankments maintained. | Integrity of Meelick, Whitesford and Boula Embankments maintained during floods and agricultural land protected for river levels up to the design crest level of the embankments. | y
| Seepage detection and repair as required for Meelick, Whitesford and Boula Embankments. There is a history of seepage developing in the material under the embankments. These seepages are repaired by grouting as required. | Meelick, Whitesford and Boula Embankments on river upstream of Lough Derg. | Ongoing | Possible requirement for National Parks and Wildlife Service licence for certain works in SACs | Integrity of approximately 20km of embankments maintained. | Integrity of Meelick, Whitesford and Boula Embankments maintained during floods and agricultural land protected for river levels up to the design crest level of the embankments. | y
| Maintenance of land drainage pumps and pumping stations and ongoing operation at Meelick, Whitesford and Boula. | Meelick, Whitesford and Boula Embankments on river upstream of Lough Derg. | Ongoing | N/A | Reliable operation of 3 No. pumping stations. | Agricultural land protected for river levels up to the design crest levels of Meelick, Whitesford and Boula Embankments. | y
| Ongoing maintenance of Fort Henry (3.1km), Ardclooney (1.2km) and Ardnacrusha Headrace Left (11.6km) and Right (11.6km) Embankments, including grass cutting, drain cleaning and repairs as required. Notes: (a) These are Category A embankments, where a breach could endanger lives in a downstream community. (b) A breach or significant damage to either Headrace Embankment would require the Headrace to be closed. The result of this would be that during a flood no water could be diverted into the Headrace and the entire flood flow would have to pass down the Shannon River channel, increasing the flood risk to areas downstream of Parteen Weir. | Fort Henry and Ardclooney Embankments upstream of Parteen Weir. Ardnacrusha Embankments on headrace canal. | Ongoing | N/A | Approximately 27.5km of embankments maintained to ensure both dam safety and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Daily inspections and seepage measurements for Fort Henry, Ardclooney and Ardnacrusha Left and Right Headrace Embankments. | Fort Henry and Ardclooney embankments upstream of Parteen Weir. Ardnacrusha embankments on headrace canal. | Ongoing | N/A | Daily inspections of approximately 27.5km of embankments and seepage measurements carried out at 138 spring measuring points and daily seepage measurements entered into Dam Monitor database. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace | y
| Monthly piezometer measurements for Fort Henry, Ardclooney and Ardnacrusha Left and Right Headrace Embankments. These measurements are taken to monitor the phreatic surface in the embankments, which influences the stability of the embankments. Alert levels are set to warn of potential stability issues. | Fort Henry and Ardclooney embankments upstream of Parteen Weir. Ardnacrusha embankments on headrace canal. | Ongoing | N/A | Monthly measurements carried out on 207 piezometers and entered into Dam Monitor database. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace | y
| Formal annual ESB inspection of Fort Henry, Ardclooney and Ardnacrusha Left and Right Headrace Embankments, comprising visual inspection of the embankments from the crest and downstream toe and review of monitoring data. | Fort Henry and Ardclooney embankments upstream of Parteen Weir. Ardnacrusha embankments on headrace canal. | Summer/Autumn 2025 | N/A | Annual inspections of Fort Henry, Ardclooney and Headrace Left and Right Embankments carried out. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace | y
| Leak detection and repairs as required at Fort Henry, Ardclooney and Ardnacrusha Left and Right Headrace Embankments. | Fort Henry and Ardclooney emmbankments upstream of Parteen Weir. Ardnacrusha embankments on headrace canal. | Ongoing | N/A | Integrity of approximately 27.5km of embankments maintained. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace | y
| Ongoing maintenance of Kilmastulla Embankment, including grass cutting and drain cleaning. | Kilmastulla embankment. | Ongoing | N/A | Integrity of approximately 2.5km of embankment maintained. | Embankment maintains its integrity during floods and protects agricultural land for river levels up to the design crest level. | n
| Daily inspection of Kilmastulla Embankment. | Kilmastulla embankment. | Ongoing | N/A | Daily inspections of approximately 2.5km of embankment carried out. | Embankment maintains its integrity during floods and protects agricultural land for river levels up to the design crest level | y
| Maintenance of land drainage pumps and pumping stations and ongoing operation at three locations along Kilmastulla Embankment. | Kilmastulla Pumphouses. | Ongoing | N/A | Reliable operation of 3 No. Pumping stations. | Protection of agricultural land for river levels up to the design crest level of embankment. | y
| Annual inspections of Ardnacrusha Headrace Bridges. | Ardnacrusha Headrace. | Autumn 2025 | N/A | Annual inspections carried out on O'Briens Bridge, Clonlara Bridge and Blackwater Bridge. | Maintenance of access routes over public road bridges. Bridges also facilitate works access to ESB dams and embankments. | y
| Daily inspections of Ardnacrusha Dam and Parteen Weir, including checking of water levels (upstream and downstream of dams), rainfall gauges and other instruments. Note: Ardnacrusha Dam and Parteen Weir are Category A dams where a breach could endanger lives in a downstream community. | Parteen Weir and Ardnacrusha Dam. | Ongoing | N/A | Daily inspections of 2 No. dams and associated gauges are carried out. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Monitoring of uplift, movements and seepages for Ardnacrusha Dam and Parteen Weir. | Parteen Weir and Ardnacrusha Dam. | Ongoing | N/A | Measurements for 98 instruments are taken at required frequencies and entered into Dam Monitor database. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Maintenance of water control gates and equipment at Ardnacrusha Dam and Parteen Weir. | Parteen Weir and Ardnacrusha Dam. | April - September 2025 | N/A | Scheduled maintenance is carried out on 7 No. spillway gates, 7 No. intake gates and 4 No. navigation gates. Gates operate as required during floods. | Water control equipment is reliable to ensure regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Formal annual ESB inspections of Ardnacrusha Dam and Parteen Weir, including visual inspection of dam structures, gates and operating mechanisms, test operation of gates, checking of gauges and review of dam monitoring data. | Parteen Weir and Ardnacrusha Dam. | Summer/Autumn 2025 | N/A | Annual inspections carried out on Ardnacrusha Dam and Parteen Weir. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Quarterly tests of headrace intake gates and spillway gate operations at Parteen Weir. | Parteen Weir. | Ongoing | N/A | Quarterly tests carried out on 6 No. spillway gates and 3 No. intake gates at Parteen Weir. | Water control equipment is reliable to ensure regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Six monthly test operation of Ardnacrusha spillway gate. | Ardnacrusha Dam. | Ongoing | N/A | Six monthly tests are carried out on the spillway gate | Water control equipment is reliable to ensure regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Annual overhauls of four turbine/generator units at Ardnacrusha Generating Station. Note: Unavailability of the turbine/generator units during a flood would result in no water being diverted into the Headrace and the entire flood flow having to pass down the Shannon River channel, increasing the flood risk to areas downstream of Parteen Weir. | Ardnacrusha Generating Station. | April-September 2025 | N/A | Annual overhauls are carried out on 4 No. turbine generator units. | Generation equipment is reliable to assist regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including ensuring that water can be diverted from the River Shannon through Ardnacrusha Headrace | y
| Annual inspection of Parteen Bridge on Ardnacrusha Tailrace. | Ardnacrusha tailrace. | Autumn 2025 | N/A | Annual inspection of Parteen Bridge is carried out | Maintenance of access route over public road bridge. Bridges also facilitate works access to ESB dams and embankments. | y
Waterways Ireland
Maintenance of sluices | Ongoing maintenance of existing sluices and gates | Ongoing maintenance of existing sluices and gates | Knockvickar (fixed weir and lock), Jamestown (fixed Weir and sluices), Jamestown (Lateral canal and lock), Rooskey (fixed weir, sluices and lock), Tarmonbarry (Fixed weir, sluices and lock), Cloondra (Fixed Weir), Meelick (fixed weir, sluices and lock) New Cut (sluices) and Athlone sluices on instruction from ESB, Operation of tilting weirs on Meelick Weir | all year |  | 9 locations inspected and maintained | proper functioning of the sluice barrages and weirs and management of water levels from a navigation perspective
Maintainance of Trails | Maintenance of recreational trails on or alongside the navigation | Maintenance and upgrade of Blueway and Greenway recreational trails on or alongside the navigations | various | all year |  | various locations adjacent to and on the navigaiton channels | safe publicly accessible recreational trails
Bord na Móna
BnM Rail Bridge at Kilnacarrow, North of Lanesborough | Periodic inspection of bridge sub-structure where deemed necessary, regarding scouring impact. | BnM Rail Bridge at Kilnacarrow, North of Lanesborough | No works envisaged at this stage for 2025, but this might change based on any inspections. | N/A | N/A | N/A | y
BnM Rail Bridge at Shannonbridge - | Periodic inspection of bridge sub-structure where deemed necessary, regarding scouring impact. | BnM Rail Bridge at Shannonbridge - | No works envisaged at this stage for 2025, but this might change based on any inspections. | N/A | N/A | N/A | y
Inland Fisheries Ireland
Consultations with Local authorities re method statements for works on bridges, weirs and site inspections | Agree designs, method statements and provide fisheries guidance on works. | Varoius Locations as required by LA other agencies | On going | Timing, methodology for the Bridge and infrastructural works will be agreed with IFI. | Appropriate structures for fish passage, negligable impact on environment during construction. | Appropriate structures for fish passage, negligable impact on environment during construction. | y
Removal of blockages from weirs, Fishpasses, fences gates and other structures where the passage of fish may be compromised. | Where resources allow possible removal by hand of trees, shrub from counter weir, other weirs, bridges,fishpasses and small streams where water would be held back and fish passage is hampered | Various locations throughout the ShRBD | As arises while on protection patrols | None required | Ensuring passage for fish and water flow | N/A | y
Maintenance of angling infrastruture to include fixed angling stands, floating angling stands, boardwalks, stiles, footbridges ,carparks and pathways | Mostly bankside or fixed to lake/river beds by posts. Generally away from flows. | Throughout the ShRBD | Year round | Core IFI activity with some external funding | Repairs to angling infrastructure | Improved angling infrastructure. Enhanced angling tourism benefit | y
Consultation with and guidance to Local Authorities and OPW re drainage activities, agreeing method statements and site inspections. | Drainage works/Capital Enhancement | Locations as required | 2025 | Details and method statements from Local Authority and OPW | channels maintained in sustainable manner | Maintain flow conditions in drainage channels, whilst having negligable impact on fisheries habitat within the watercourse. | y
All County Councils
Repairs to Bridges & Culverts and Maintenance of embankments and pumping stations See examples below | Drainage Districts - carry out annual inspections on bridge\culverts along drainage district. | Various Locations | Varies | Possible requirement for National Parks and Wildlife, Inland Fisheries,OPW & Landowners for certain works. | Varies | Facilitates natural stream drainage, reduces risk of localised flooding | y
Leitrim County Council
Hartley Bridge | Construction of new bridge at Hartley over River Shannon | Hartley Carrick on Shannon | This project is currently at Detail Design and Tender Docs preparation Stage | Approval required from TII to proceed to tender | Subject to funding approval from the TII. | Replacement bridge over the River Shannon at Hartley | n

## Maintenance of Channels
Maintenance of Channels | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Responsibilities
ESB
| Cleaning of screens at inlets to culverts and siphons on rivers and streams draining under Ardnacrusha Headrace during floods. | Ardnacrusha Headrace. | Ongoing - as required | N/A | Screens kept clean, particularly during floods. | Facilitates natural stream drainage, reduces risk of localised flooding and protects Headrace Embankments | y
| Annual cleaning of Kilmastulla River adjacent to Fort Henry Embankment (2.5km) and Black River and open drain (1km) adjacent to Ardclooney Embankment. | Fort Henry and Ardclooney Embankments upstream of Parteen Weir. | Summer/Autumn 2025 | N/A | Approximately 3.5km of channels cleaned. | Facilitates channel conveyance, reduces risk of localised flooding and protects Headrace Embankments. | y
Inland Fisheries Ireland
Consultation with and guidance to Local Authorities and OPW re drainage activities, agreeing method statements and site inspections. | Drainage works/Capital Enhancement | Locations as required | 2025 | Details and method statements from Local Authority and OPW | Channels maintained in sustainable manner | Maintain flow conditions in drainage channels, whilst having negligable impact on fisheries habitat within the watercourse. | Y
Waterways Ireland
Maintenance of navigation channel | Ongoing and planned maintenance of channel including removal of obstructions,debris, weed cutting and cutting back of vegitation impacting the navigation channel. Maintenance of Navigation aids(1350) | various | all year |  | 250km of channel maintained | Ensure navigation channel is clear for navigation - while reducing risk of flooding | y
Office of Public Works
Arterial Drainage Maintenance: The Commissioners of Public Works have a duty under Section 37 of the Arterial Drainage Act, 1945 to maintain drainage works carried out under said Act "in proper repair and and effective condition". | In 2025, approx 883kms of channels and embankments will be maintained. | In 2025, approx 883kms of channels and embankments are to be maintained on the following schemes: Boyle, Knockcroghery, Inny, Brosna, Killimor/Cappagh, Carrigahorig, Nenagh/Clareen, Mulkear, Groody, Ballynaclogh, Maigue, Deel, Feale, and those embankment schemes administered collectively by OPW as Shannon Embankments North and Shannon Embankments South. Progress will to be reported on quarterly. | Ongoing throughout the year. | We have agreed protocols with IFI and consult with DAHG (NPWS) on Habitats Directive requirements and DAHG (DAU) on possible impact on Archaeology. Appropriate Assessments must be carried out where our work is likely to have a significant effect on an SAC. In the event that species covered by the Wildlife Act are to be the subject of interference licences need to sought from NPWS. | 883kms of channels and embankments maintained. | The Programme ensures that flood risk in these cases is kept at the current relatively low level. | n
Joint initiative led by OPW and Waterways Ireland | Progress the development of a proposal for the removal of a series of pinchpoints or constrictions in the navigation channel between Meelick Weir and Athlone, in the Callows area. | Callows | Ongoing | Requires a hydraulic analysis, environmental assessment under the appropriate legislation and will be subject to planning. The required planning process would be a matter for Waterways Ireland. As part of the development of this proposal, the potential impact on flows will be assessed to ensure that any works do not have a negative impact further downstream. |  | Improvement to channel conveyance with reduction in water levels and flood risk. | n
All County Councils
Maintain Arterial Drainage schemes that are the responsibility of the Local Authority and other channel maintenance. See examples below | Drainage Districts - removal of vegetation and blockages to small rivers, streams and drains | Various Locations | May to September | Possible requirement for National Parks and Wildlife, Inland Fisheries, OPW & Landowners for certain works. | Possible requirement for National Parks and Wildlife, Inland Fisheries, OPW & Landowners for certain works. | Possible requirement for National Parks and Wildlife, Inland Fisheries, OPW & Landowners for certain works. | y
Leitrim County Council
Responsibility for a number of Drainage Districts under the Arterial Drainage Acts | Channel clearing | Rinn and Black River DD - area Cloone | Ongoing | Agreement with landowners and Inland Fisheries, subject to funding approval | 12 km planned to be cleaned in 2025 | Maintain flow conditions in drainage channels | y
Responsibility for a number of Drainage Districts under the Arterial Drainage Acts | Responsibility for a number of Drainage Districts under the Arterial Drainage Acts | Ballinamore / Ballyconnell DD - area Aghanasheelin | Ongoing | Agreement with landowners and Inland Fisheries, subject to funding approval | 10 km planned to be cleaned in 2025 | Maintain flow conditions in drainage channels | y
Responsibility for a number of Drainage Districts under the Arterial Drainage Acts | Channel clearing | Headford DD | Ongoing | Agreement with landowners and Inland Fisheries, subject to funding approval | 5 km planned to be cleaned in 2025 | Maintain flow conditions in drainage channels | y
Responsibility for a number of Drainage Districts under the Arterial Drainage Acts | Channel clearing | Eslin DD - area Kilnagross | Ongoing | Agreement with landowners and Inland Fisheries, subject to funding approval | 5 km planned to be cleaned in 2025 | Maintain flow conditions in drainage channels | y
Limerick City & County Council
Mulkear River | Maintenance of Mulkear River | Between Abington bridge and Derraun bridge (R507). Along Mulkear river, Reask river, Dead river and associated channels and drains | Works for 2025 on going (€136,k Funded through Environmentdue to the 1955 Arterial Drainage Act | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | 30km of channel to be maintained including tributaries. Works are planned year on year with annual returns to IFI | Maintain flow conditions in drainage channels. Chemical weed spraying to remove Japanese knot weed, Giant Hogweed. Remove vegetation along the tributory channels. Repairing of eroded or breached banks. Improve conditions for Salmon, lamprey and Otter. Note Mulkear, Dead and Reask rivers are in SAC. | n
Galway County Council
Ahascragh Drainage District | Maintenace of the Bunowen/Ahascragh River System | Upstream of Killsolan | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Removal of debris and clearing of blockages in drainage channels. Approx 1.5km cleaned in Killosolan Area. | Maintain flow conditions in drainage channels | n
Mountbellew Drainage District | Maintenance of the Castlegar/Shiven River System | Various Locations | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | 1km of channel to be cleaned and blockages removed | Maintain flow conditions in drainage channels | n
Mountbellew Drainage District | Bridge repair/replacement at Ballinlass/Tirur | Ballinlass/Tirur | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Bridge repair | Maintain flow conditions in drainage channels | n
Meelick/Polshask Drainage District | Maintenance of the Meelick / Polshask River System | Various Locations | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Removal of debris and clearing of blockages in drainage channels | Maintain flow conditions in drainage channels | n
Kellysgrove Drainage District | Inspection & Monitoring of culvert / bridge on Cloonascragh River | Lismay townland | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Improvement works to culvert / bridge if deemed required to maintain/improve flow. | Improve and Maintain flow conditions in the River Shannon and mitigate a potential cause of flood risk | n
Kellysgrove Drainage District | Maintenance of the Cloonascragh/Ballinure River System | Downstream of Ballinure Bridge | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Approx 1km of channel to be cleaned and bridge repairs | Maintain flow conditions in drainage channels | n
Suck Drainage District | Drainage Districts - removal of vegetation and blockages to small rivers, streams and drains | Channels into the Bunowen River, Sonnagh & Killure beg Townland | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Approx 0.5km of channel cleaned | Maintain flow conditions in drainage channels
Suck Drainage District | Maintenance of the Deerpark River System | Downstream of Ballinasloe Railway Station Bridge | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Approx 0.5km of channel cleaned | Maintain flow conditions in drainage channels - reduce flood risk | n
Suck Drainage District | Temporaray Flood defence system improvement | Ballinasloe Town | 2025 | Subject to any necessary Environmental Screening & consultation & agreement with Landowners, NPWS & IFI | Reapir & maintenance of Aquadam temporary flood defence equipment, and purchase of new Aquadam section to improve deployment. | Improve flood defences
Clare County Council
Confluence of Mulkere River with the River Shannon | CCC have a serious concern that significant silting occurs at the confluence of the flashy Mulkere River and the much slower moving River Shannon River. Consequently, this restriction may cause flooding upstream. This is being progressed by Office of Public Works and a multi agency group at Present. | Confluence of Mulkere River with the River Shannon | As required subject to assessment | Subject to any necessary Environmental Screening & consultation & agreement with NPWS & IFI | Significant potential for risk upstream will be eliminated | Improve and Maintain flow conditions in the River Shannon and mitigate a potential cause of flood risk | Improve and Maintain flow conditions in the River Shannon and mitigate a potential cause of flood risk

## Water Level and Flow Regulation
Water Level and Flow Regulation | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity | Details of the expected outcome from this activity | Roles and Responsibilities
ESB
| Operation of four turbine generator sets at Ardnacrusha Generating Station for electricity production | Ardnacrusha Generating Station. | Ongoing | Generation Licence (CER). | Output is electricity generation. Up to 400 cubic metres per second flows in headrace at full load. | Diversion of water to Ardnacrusha Generating Station via headrace canal means that it is not flowing down the original Shannon course south of Parteen Weir. This provides flood benefit in this area. | y
| Regulation of discharge at outlet from Lough Allen. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Ongoing as lake levels vary | N/A | Water control equipment operated to regulate water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. Note that lake levels are varied for the purposes of ensuring minimum navigation levels in summer and to maintain minimum flow in the downstream channel. Maximum level is set by embankment safety consideration. | y
| Ongoing assessment, ecological surveys, drone mapping, hydrological data collection (and implementation if licensed ) of pilot protocol for regulating water levels in Lough Allen during the winter period. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Ongoing from September - end February, as weather conditions and inflows allow. | Secttion 21 License from NPWS | Water control equipment operated to regulate water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Regulation of water levels in Lough Allen in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. Note that lake levels are varied for the purposes of ensuring minimum navigation levels in summer and to maintain minimum flow in the downstream channel. Maximum level is set by embankment safety consideration. | y
| Regulation of discharge at outlet from Lough Ree by Waterways Ireland under instruction from ESB. Note that ESB exercises no control on Lough Ree water levels during floods when all sluices gates on Athlone Weir are closed. | Athlone Weir at southern end of Lough Ree. | Ongoing as lake levels vary | N/A | Water levels in Lough Ree are regulated in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including the agreed interim guidelines between April and mid-August. | Regulation of water levels in Lough Ree in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including the agreed interim guidelines between April and mid-August. Note that lake levels are varied for the purposes of ensuring minimum navigation levels in summer. | y
| Trial implementation and ongoing assessment of interim guidelines for regulating water levels in Lough Ree between April and mid-August. | Athlone Weir at southern end of Lough Ree. | Ongoing as lake levels vary | N/A | Water levels in Lough Ree are regulated in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including the agreed interim guidelines between April and mid-August. | Regulation of water levels in Lough Ree in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including the agreed interim guidelines between April and mid-August. Note that lake levels are varied for the purposes of ensuring minimum navigation levels in summer. | n
| Continuous monitoring of water levels and rates of drawdown in Parteen Basin and Ardnacrusha Headrace to ensure embankment stability. Levels either above maximum allowed or below minimum allowed can have adverse effects on the stability of Fort Henry, Ardclooney and Ardnacrusha Left and Right Headrace Embankments. | Fort Henry and Ardclooney embankments upstream of Parteen Weir. Ardnacrusha embankments on headrace canal. | Ongoing | N/A | Integrity of approximately 27.5km of embankments maintained. | Maintenance of embankment safety, prevention of inundation due to embankment breaches and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Regulation of discharge at the outlet from Lough Derg. | Parteen Weir. | Ongoing as lake levels vary | N/A | Water levels in Lough Derg regulated in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon. | Maintenance of dam safety, prevention of inundation due to dam failure and regulation of water levels in Lough Derg and Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Implementation of the requirements of the Regulations and Guidelines for the Control of the River Shannon, at all times, but particularly during flood periods. | N/A | Ongoing | N/A | Water management is carried out in accordance with the Regulations and Guidelines for the Control of the River Shannon. | Maintenance of dam and embankment safety, prevention of inundation due to dam failure or embankment breaches and regulation of water levels in Loughs Allen, Ree and Derg, as well as in Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon and interim/pilot measures in place for Loughs Allen and Ree, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
| Daily management of water levels in Loughs Allen, Ree and Derg. | N/A | Ongoing | N/A | Daily generation targets prepared, sluice gates adjusted as required at Bellantra Sluices, instructions given to Waterways Ireland regarding required changes to sluice gates at Athlone Weir and spilway gates adjusted as required at Parteen Weir. | Ensures regulation of water levels in Loughs Allen, Ree and Derg, as well as in Parteen Basin in accordance with ESB's Regulations and Guidelines for the Control of the River Shannon and interim/pilot measures in place for Loughs Allen and Ree, including diversion of water from the River Shannon through Ardnacrusha Headrace. | y
Waterways Ireland
Management of water levels | Management of water levels at 9 structures to defined Ordinary Summer Level and within defined limits in conjunction with ESB. Recording of water levels rainfall etc on each section of navigation channels | Knockvickar (fixed weir and lock), Jamestown (fixed Weir and sluices), Jamestown (Lateral canal and lock), Rooskey (fixed weir, sluices and lock), Tarmonbarry (Fixed weir, sluices and lock) Clondra (fixed Weir, Meelick (Fixed Weir, tilting weir operation, Sluices and Lock, New Cut Sluices and Athlone (Fixed Weir and Sluices) under instruction from ESB | ongoing |  | water level managed daily in conjunction with ESB | water level managed daily to maintain navigable channel levels | y
Inland Fisheries Ireland
| Review abstraction proposals to ensure fish passage and protect fish and aquatic life against unnatural fluctuations in water levels | Locations as required | 0 | As abstraction licences are applied for | Ensuring fish passage and wetted areas for fish spawning | Conservation of fish stocks and protection of the aquatic life | y

## Hydrometric Monitoring
Hydrometric Monitoring and Forecasting | From your Agency's 2024 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Responsibilities
ESB
| Daily recording of Lough Allen water levels and rainfall. | Bellantra Sluice Structure, Lough Allen, Co.Leitrim. | Ongoing | N/A | Daily record of Lough Allen water levels and rainfall. | Daily monitoring and recording of hydrometric data provides essential input to water management decisions, particularly during floods. | y
| Daily recording of Lough Ree water levels. | "The Thatch" water level gauge on eastern side of Lough Ree. | Ongoing | N/A | Daily record of Lough Ree water levels. | Daily monitoring and recording of water levels provides essential input to water management decisions, particularly during floods. | y
| Daily recording of Lough Derg water levels and rainfall. | Portumna, Ballyvalley and Pier Head (Killaloe). | Ongoing | N/A | Daily record of Lough Derg water levels and rainfall. | Daily monitoring and recording of hydrometric data provides essential input to water management decisions, particularly during floods | y
| Monitoring of levels and alarms, upstream of culverts and siphons, on seven rivers and streams draining under Ardnacrusha Headrace. | Ardnacrusha Headrace. | Ongoing | N/A | Continuous monitoring of levels and alarms. | Facilitates natural stream drainage, reduces risk of localised flooding and protects Headrace Embankments | y
| Twice weekly forecasts of water levels in Loughs Allen, Ree and Derg. | N/A | Ongoing | N/A | Lake level forecasts prepared and link issued to stakeholders on Mondays and Thursdays. | Lake level forecasts assist stakeholders in preparing for potential adverse conditions during floods or low levels. | y
| Provide hydrometric data for the Shannon in response to queries from the public, state and sem-state organisations, consultants, academic institutions, etc. | N/A | Ongoing | N/A | Responses provided to queries in a timely manner. | Data provided in response to queries assist in flood risk management for new and existing developments. | y
| Display daily level data for ESB gauges on the Shannon, daily flow data for Ardnacrusha and Parteen Weir and the current twice weekly forecast on the ESB website. | https://esb.ie/what-we-do/generation-and-trading/hydrometric-information | Ongoing | N/A | Data updated on a daily basis. | Level and flow data publically available at all times, including during floods. | y
Office of Public Works
OPW Hydrometric Programme | There are 119 active hydrometric station in hydrometric regions 24-28. There are also two rain gauges at Kilkee and at Cullen, Co Tipp. | www.waterlevel.ie | Ongoing | None | Continuous monitoring of water levels | Helps quantify severity of event and aids all organisations in provision and management of flood response measures. | y
Environmental Protection Agency
Hydrometric Monitoring and Public Information | Implementation of the EPA hydrometric monitoring programme within the Shannon Catchment with a focus on monitoring of low flows. EPA provides support to OPW staff during flooding events when requested. EPA operates a website (Hydronet that acts as a portal to all hydrometric monitoring sites nationally) and produces a monthly national hydrology bulletin that incorporates data from the various flow monitoring agencies. | https://epawebapp.epa.ie/hydronet/ | Ongoing | Maintenance of hydrometric stations by LAs | Completion of the hydrometric monitoring programme in the Shannon Catchment | Improved hydrometric data on the flow regime within the Shannon. | y

## Regulatory Functions
Regulatory Functions | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Responsibilities
Waterways Ireland
Navigation Authority | Waterways Ireland is the navigation authority with responsibility for the management, maintenance, development and restoration of the Shannon Navigation | 250km of navigation channel and asociated facilities and infrastructure | As appropriate | As required | Manage and maintain the navigation | Support cruise hire industry, private boating sector and the recreation and tourism sectors in general | y
National Parks & Wildlife Service
Government Department with responsibilty regarding oversight of the implementation of the Habitats and Birds Directives, the Wildlife Acts 1976 to 2000, and the National Biodiversity Plan. | Prescribed body under Planning and Developments in respect of Appropriate Assessment. Referal body under Regulation 42(10) EC (Birds and Habitats) Regulations 2011 in respect of AA and public authorities' own plans and projects. |  | As appropriate | As required |  |  | y
Licence Authority | Licence authority in relation to various flora, fauna and habitats under the EC(Birds and Natural Habitats) Regulations 2011 (Regulation 54 and 55). |  | As appropriate | As required |  |  | y
Consent Authority | Consent authority for "Activtities Requiring Consent" under Regulation 28 of the EC(Birds and Natural Habitats) Regulations 2011, the Wildlife Acts, the Biodiversity & National Biodiversity Plan where in some cases certain works proposed to be undertaken by non public bodies require the consent of the Minister. |  | As appropriate | As required |  |  | y
Office of Public Works
Consent Authority | S47 and S50 Arterial Drainage Act prohibit the alteration or erection of weirs and bridges without the prior consent of the Commissioners. (The ESB has a derogation in the case of the former as do works carried out under certain provisions of Fisheries legislation.) | Defined by each individual application. | Ongoing throughout the year. | No consent may be given without prior consultation with The Minister for Agriculture or in contravention of certain orders made of notices served under certain Fisheries Acts. | Decision within 8 weeks of receipt of complete application. | These consents reduce enormously the risk that flooding might arise from the inappropriate erection or alteration of the classes of structures covered. | y
Inland Fisheries Ireland
State's Inland Fisheries Agency working with regulatory functions of the Fisheries Acts and associated regulations | IFI is the state agency responsible for the protection , management and conservation of Ireland's inland fisheries and sea angling resources | Various | Various |  |  | No impact on flooding | y
Environmental Protection Agency
Authorisation of waste activities (EPA and Local Authorities) | Regulation of waste activities. The Environmental Protection Agency is responsible for the authorisation of all large scale waste disposal and recovery activities. Local authorities are responsible for the authorisation of all other (usually smaller scale) waste activities. The EPA is the competent authority for determining the correct form of authorisation for any individual proposed waste activity. The deposition of waste dredge spoil on land is a waste activity. There are some exemptions from waste authorisation available (namely and for example section 3 of the Waste Management Act) but these are restrictive in their scope. | Waste disposal and recovery facilities, e.g. deposition sites for waste dredged spoil. Location of disposal and recovery facilities to be determined by project owners. | Prior to commencement of waste deposition, a waste authorisation must be in place. | Operators undertaking a waste activity must apply for and obtain the correct authorisation in advance of commencing the activity. A Waste licence is required for deposition of waste dredge spoil where the capacity of the deposition site exceeds 100,000 tonnes. A waste facility permit or certificate of authorisation will be required if the capacity of the deposition site is <100,000 or <25,000 tonnes respectively. A query as to the appropriate form of authorisation for any individual deposition site can be directed to the EPA's Environmental Licensing Programme. | Number of decisions on waste applications relating to deposition of waste dredged soil | Appropriate authorisation of waste activities and management of associated environmental risks. | y
Authorisation and enforcement of peat extraction licences | Approval of bog rehabilitation plans prepared by Bord na Mona. | Authorised (IPC licence) peat extraction sites | Per BnM's schedule | Submission by BnM of rehabilitation plans for EPA approval | Number of approved bog rehabilitation plans | Outcome is rehabilitated cutaway bogs, leading ultimately to surrender of peat extraction licences. Some rehabilitated bogs will have participated in the Peatlands Climate Action Scheme (https://www.bnmpcas.ie/) and enhanced rehabilitation (climate action) may have taken place. | y
Authorisation and enforcement of water abstractions and associated impoundments | Regulation of water abstractions. The Environmental Protection Agency is responsible for the authorisation and enforcement of all water abstractions greater than 2,000 m3/d and any significant abstractions between 25-1,999 m3/d. Local authorities are responsible for ensuring all other water abstractions are not impacting on the environment. | Authorised water abstractions | Ongoing as applications are submitted to the EPA | Submission of water abstraction license requests from relevant abstractors for EPA consideration and approval | Number of abstraction licenses issued | The EPA will have finalised its water abstractions ICT portal and associated licensing guidance, with appropriate authorisation of water abstraction applications thereafter.
All County Councils
Planning and Development Regulations 2001 | Planning Control | Various | This can occur at any time | N/A | N/A | N/A | y
Limerick City & County Council
Limerick City & County Council Draft Development Plan 2022-2028 | New Development Plan including Strategic Flood Risk Assessment completed in draft 2021. Subject to adoption in 2022. The outputs of the hydraulic modelling and flood extents generated through the Limerick FRS may be considered as a basis for updating the Strategic Flood Risk Assessment completed in draft 2021. | City Countywide (with the exception of a number of LAPs) | Ongoing | None | Better decision making on development proposals | Proper planning principles with respect to flood risk management and flood resilience | n
Local Area Plans - LAPs | Several LAP's to be updated in 2022 including towns of Newcastle West and Abbeyfeale | Caherconlish, Castleconnell, NCW, Abbeyfeale and others | Ongoing | None | Better decision making on development proposals |  | n
Clare County Council
Clare County Council Development Plan 2023 - 2029 | The recently adopted Clare County Development Plan 2023 - 2029 includes Volume 10c Stratgeic Flood Risk Assessment. | Countywide | ongoing | None | Better decision making on development proposals | Proper planning principles with respect to flood risk management and flood resilience | n

## Mapping, Planning and Emergency
Mapping, Planning and Emergency | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where will this activity occur | When will this activity occur | External factor(s) necessary to complete this activity | Details of the expected output from this activity. This will be the KPI for this activity. | Details of the expected outcome from this activity | Roles and Responisbilites
Office of Public Works
Mapping | Ongoing review and update of flood maps, as necessary | www.floodinfo.ie | Ongoing | Statutory Instrument(s) transposing the 'Floods' Direcitve | Up-to-Date flood maps | Inform Emergency Response Planning, Development of Resilience, Sustainable Planning and climate Adaptation Planning | y
Inland Fisheries Ireland
Identifying barriers to fish passage on River Shannon | Assessment of barriers to fish movement | Ongoing | Ongoing | None required | Mapping barriers to fish migration | Identifying barriers to fish migration | y
All County Councils
Emergency | Flood incident management on Public Property and to assist in the protection of private property | Various Locations | Varies | Possible requirement for National Parks and Wildlife, Inland fisheries,OPW & Landowners for certain works. | Varies | Protection of property | y
Emergency | Crisis Management Process at local level on inter-agency basis | As required where weather events are forecasted / occur | As required when weather events are forecasted / occur |  | Emergency response plans implemented | Manage response to Flooding effectively | y
Leitrim County Council
Emergency | Crisis Management Process at local level on interagency basis | Leitrim Flood Management Response Team meets daily during emergencies in response to flood events. Liaises with OPW and ESB re water levels etc. | As required when weather events are forecasted / occur |  | Manage response to Flooding effectively | Protection of properties, keeping roads and pedestrian access open. | y

## WFD and Climate Change
Water Framework Directive and Climate Change | From your Agency's 2025 Work Programme, describe the activities that relate to or impact flooding, flood risk or flood risk management of the Shannon River Basin District | Where on the Shannon Catchment will this activity occur | When will this activity occur | External Factor(s) necessary to complete this Activity | Details of the Expected Output from this Activity. This will be the Output KPI for this activity. | Details of the Expected Outcome from this Activity. | Roles and Responsibilities
Inland Fisheries Ireland
Drainage or Flood alleviation works | Consultation in relation to Flood Relief Schemes and associated Planning to ensure compliance with WFD and Fisheries Legislation as they arise. | Various | Ongoing as necessary | EIS, AA, Approvals |  |  | y
Lough sheelin climate change databouy | Continuous monitoring programme recording water temperatures, dissolved oxygen and chlorophyl levels on the lake and temperature and dissolved oxygen on the Rivers. | Lough Sheelin, River Inny and Mount Nugent River | ongoing | In conjunction with OPW funding |  | Inofrmation and research data and reports, along with a public facing web access to data once validated. | y
Environmental Protection Agency
EPA Research | EPA Research Activities assist in informing policy on the areas of Climate Change Adaptation & Mitigation, Water Quality, WFD (objectives/POMS) and Catchment Management. | n/a | ongoing | n/a | n/a | Research reports, data, resources etc, all available open source. 1. EPA Research Reports: https://www.epa.ie/our-services/research/epa-funded-research/epa-research-publications/ 2. EPA Research Projects Database: https://eparesearch.epa.ie/smartsimple/ - The EPA has funded over 1,000 projects. This database contains information about all of these projects and is searchable by: keywords, lead researcher, research institution etc. This database also provides details of the project abstract, expected end date and where relevant a link to the final report/output. 3. EPA Research Data Archive (SAFER database): https://eparesearch.epa.ie/safer/ : SAFER-Data is a fully web-based interface to the EPA's Environmental Research Data Archive. Information is presented on SAFER-Data as a "resource" and any related datasets or information objects that are publicly available for download. The goal of SAFER is to provide open access to the environmental research data to citizens, academics, policy makers, researchers, etc in Ireland and around the world. | y
Water Framework Directive Implementation | The EPA will continue to provide the evidence base on the pressures and impacts on waters, and provide advice to DHLGH on the setting of WFD environmental objectives and the programme of measures as reported in the river basin management plan. | Whole catchment | ongoing | Water Body Risk Characterisation and Classification elements completed by other public authorities, as required under the WFD | Water Body information updated | Updated water body status (2019-24) and associated information reported on programmes of measures, environmental objectives and updated assessments on risk of failing to meet the environmental objectives.
Office of Public Works
Floods' Directive - WFD Coordination | The OPW will continue to coordinate with the EPA and the D/HLGH on the ongoing implementation of the FD/WFD, including bi-lateral meetings, cross-representation of the OPW on the WFD management groups and vice-versa, the exchange of relevant information and the assessment of measures that may provide multiple benefits. | This action applies primarily to the measures proposed for the 67 communities for which flood maps were prepared in the 1st cycle of the Floods directive implementation, but also to their catchments and more broadly thoughout the River Basin. | Ongoing | Requirements of the 'Floods' and Water Framework Directives | WFD-compliant flood risk management measures where proposed / implemented | Where possible, measures that will have benefits for both WFD and flood risk management objectives and to identify and address measures that may otherwise cause conflict between the objectives of the two Directives | y
Climate Change Adaptation | The OPW considers the possible impacts of climate change, and the associated uncertainty in projections, at all stages of activity under the national Flood Risk Management Programme, and the development, design and implementation of all policies, strategies, plans and measures for, or related to, flood risk management must be sustainable and cognisant of the potential impacts of climate change. | This action applies thoughout the River Basin. The National Indicative Fluvial Mapping project has been completed, providing potential future scenario flood extents as well as those for the current scenario, for all reaches with a catchment greater than 5km2. | Ongoing | National Adaptation Framework (under the Climate Act 2015) | Flood maps for potential future scenarios taking account of the potential impacts of climate change - Refer to www.floodinfo.ie | Robust, sustainable and adaptable flood rsk management strategies and measures. | y
Bord na Mona
Peatland rehabilitation and restoration (Peatlands Climate Action Scheme) | Continuation of rehabilitation of peatlands in the Shannon catchment at Blackwater, Mountdillon and Derrygreenagh Bogs, as required under condition 10 of Integrated Pollution Control Licence under Section 83(3) of the Environmental Protection Agency Act, 1992, and associated enhanced rehabilitation under the PCAS scheme. | Peatlands in the Shannon (Upper & Lower), SHANNON (Upper)_070, GORTGALLAN_010, SHANNON (Upper)_100, SHANNON (Upper)_120 and BLACKWATER (SHANNONBRIDGE)_020, Feorish, Ballynakill, Lough Bannow, Ledwithstown, Boor, Curraghboy, Silver and Brosna water body catchments. | Ongoing in 2025 | Stakeholder Consultation, Bog Rehabilitation Plans, AA Screening and DECC/NPWS/EPA Approvals | Hectares rehabilitated | Returning of these peatlands to their natural water retention function which will assist in the reduction of peak run-off to receiving waters in the Shannon catchment | y
Waterways Ireland
Climate Mitigation | Ongoing Implementation of Energy Audit recommendations and other energy efficiency measures. | Throughout the Shannon Navigation as required | ongoing in 2025 |  | Reduction in GHGs and improvement in energy efficiency | Targeted measures to reduce GHGs forming part of the WI Climate Action Plan implementation. | n
Climate Adaptation | Climate Impact Assessment complete and being used to inform future adaptation measures. | Throughout the Shannon Navigation | ongoing in 2025 |  | Strategic planning for assets at risk from climate change | Robust, sustainable and adaptable management of assets at risk. | n
Water Framework Directive Implementation | Ensure continued compliance of Shannon Navigation Maintenance and Capital Works, per our statutory remit, with the Water Framework Directive. Participation in National WFD Steering Groups, providing specialist knowledge and keeping abreast of latest developments | Throughout the Shannon Navigation | ongoing in 2025 | Requirements of the Water Framework Directives | Compliance with the Water Framework Directive | Full compliance with the Water Framework Directive | y